## Slide 1: Recommendations for Civilian Investigators Conducting Human Studies in the Military
Craig Formby, Ph.D.
Distinguished Graduate Research Professor Emeritus
University of Alabama
Auburn University October 4, 2019

## Slide 2: Recommendations
Work closely with knowledgeable and enthusiastic military officials to identify appropriate study sites
Obtain commitments for the study from enthusiastic site investigators and as much of the full chain of command as possible before requesting funding
Because of the transitional nature of the military, anticipate greater participant attrition and missed study visits than for corresponding studies conducted in civilian clinical centers; therefore, power your study accordingly and anticipate a longer study duration to achieve the target study sample

## Slide 3: Recommendations
After funding is attained, initiate processes early on to prepare Cooperative Research and Development Agreements (CRADAs) and to obtain IRB approvals (simultaneously, if allowed ); be prepared to be patient with these processes
Recruit and cross train study personnel, providing for redundancy in key study personnel
Consider hiring civilian study staff, but be prepared for lengthy intervals between hiring and approval of their security clearances

## Slide 4: Recommendations
Anticipate ongoing training of study personnel due to the transitional nature of military personnel
For long-term studies, plan for continued care and data collection after study participants are reposted or after they separate from the military and can no longer be treated at a military facility
Plan flexible recruitment strategies in anticipation that each study site may have different and changing requirements for posting and allowing for recruitment materials to be dispersed

## Slide 5: Recommendations
Anticipate challenges transferring study data through clinical center firewalls, which may limit the utility of web-based data systems and off-site repositories
Anticipate challenges arranging for base access and expect delays when entering military study sites
Anticipate challenges paying civilian study personnel, purchasing study equipment and supplies, and arranging study-related travel within the military system

## Slide 6: Recommendations
Be prepared for military priorities to take precedence over study protocols, especially last minute cancellation of study visits
Expect the unexpected-wars, furloughs, base closures, restrictions affecting study participation, transfers of study personnel and participants, change in military priorities and site/command commitments leading to loss of study sites

## Slide 7: Acknowledgements
This presentation was adapted from “Lessons learned conducting a multi-center trial with a military population: The Tinnitus Retraining Therapy Trial”, Clinical Trials, published online, May 2018. (Available as a handout)
Support for preparation of the above report was provided by NIH awards U01DC007411 (C. Formby, Study Chair) and U01DC007422 (R.W. Scherer, Data Coordinating Center Director).